## Intro & Contents
[Client] Project Hub
What is a project hub?
This workbook is a living document containing a number of key artifacts and planning tools for the project.
What's in this project hub?
Project Documentation | Important or frequently referenced documentation for quick access.
Project Schedule | A detailed schedule of the site design and development phases.
Functional Requirements | The functional requirements represent features and interactions that can occur on the site and need to be accounted for in scope planning/
Technical Requirements | The technical requirements represent specific technical or compliancy needs identified during discovery that will be included in the final deliverables.
User Types & Top Needs | Each of the users/personas identified and their requirements.
Web Content Project Plan | A planning document for all pages, this includes the status of each along with relevant details.
Redirect Mapping | Any legacy URLs will require a redirect for launch if the path is changing or the page is being omitted.
QA List | An ongoing list of open tasks and issues that need addressed for all parties involved

## Project Documentation
Project Documentation
What important or frequently referenced documentation do we have available?
Document Name | Description
Discovery Documentation Guide | A summary of all pre-existing research and recommendations from the discovery process.
Interview Guides | A folder with all interview guides for discovery interviews
Competitive Analysis | Website UX-focused competitive analysis completed by ExpandTheRoom
Site Map | Slickplan site map
Wireframe Deliverables
Page Name | Wireframe URLs | Approval Status
Homepage | Desktop: Mobile: | Not started
Landing Pages: | [Listed below] | Not started
Desktop: Mobile: |  | Not started
Landing Page 2 | Desktop: Mobile: | Not started
Design Deliverables
Page Name | Wireframe URLs | Approval Status
Homepage | Desktop: Mobile: | Not started
Landing Pages: | [Listed below] | Not started
Desktop: Mobile: |  | Not started
Landing Page 2 | Desktop: Mobile: | Not started

## Project Schedule
|  |  |  | Week 1* | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40 | [6 empty] | Week 41 | [6 empty] | Week 42
|  |  |  | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | Sat | Sun
|  |  |  | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13 | 2021-08-14 | 2021-08-15 | 2021-08-16 | 2021-08-17 | 2021-08-18 | 2021-08-19 | 2021-08-20 | 2021-08-21 | 2021-08-22 | 2021-08-23 | 2021-08-24 | 2021-08-25 | 2021-08-26 | 2021-08-27 | 2021-08-28 | 2021-08-29 | 2021-08-30 | 2021-08-31 | 2021-09-01 | 2021-09-02 | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2021-09-06 | 2021-09-07 | 2021-09-08 | 2021-09-09 | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2021-09-13 | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 | 2021-09-19 | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26 | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2022-01-01 | 2022-01-02 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08 | 2022-01-09 | 2022-01-10 | 2022-01-11 | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28 | 2022-01-29 | 2022-01-30 | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | 2022-05-16 | 2022-05-17 | 2022-05-18 | 2022-05-19 | 2022-05-20 | 2022-05-21 | 2022-05-22 | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | 2022-05-23 | 2022-05-24
Discovery Process | bar: Week 1* M
| 1 | Discovery kickoff | 2021-08-11 | bar: Week 1* W
| 1.1 | Review relevant pre-existing materials | 8/11-8/16 | bar: Week 1* W to Week 2 M
| 1.2 | Stakeholder interviews (inc delay) | 8/17-9/28 | bar: Week 2 T to Week 3 F; Week 4 M to Week 4 F; Week 5 M to Week 5 F; Week 6 M to Week 6 F; Week 7 M to Week 7 F; Week 8 M to Week 8 T
| 1.3 | Competitive analysis | 8/23-9/1 | bar: Week 3 M to Week 4 W
| 1.4 | Caregiver user interviews | 9/3-9/13 | bar: Week 4 F to Week 6 M
| 1.5 | Patient user interviews | 9/22-10/1 | bar: Week 7 W to Week 7 F; Week 8 M to Week 8 F
| 1.6 | Customer and prospect interviews | 9/27-10/1 | bar: Week 8 M to Week 8 F
| 1.7 | ELT (CEO/CXO) interviews (tent.) | 9/27-10/1 | bar: Week 8 M to Week 8 F
| 1.8 | CHHA interviews (added request) | 10/4-10/6 | bar: Week 9 M to Week 9 F
| 1.9 | SEO audit and analytics review | 10/8-10/13 | bar: Week 9 F; Week 10 M to Week 10 W
| 1.1 | Keyword research & gap analysis | 10/11-10/15 | bar: Week 10 M to Week 10 F
| 1.11 | Generate proposed IA including site map | 10/18-10/20 | bar: Week 11 M to Week 11 W
| 1.12 | Draft core design requirements and core user stories | 10/21-11/8 | bar: Week 11 Th to Week 11 F; Week 12 M to Week 12 F; Week 13 M to Week 13 F; Week 14 M to Week 14 T
| 1.13 | Core team read-out presentation for sign-off | 2021-11-09 | bar: Week 14 T
| 1.14 | Discovery findings deck and read-out presentation #1 - Informative | 2021-11-16 | bar: Week 14 F
| 1.15 | Discovery findings deck and read-out presentation #2 - Informative | 2021-11-19 | bar: Week 15 F
| 1.16 | Note: *Milestones must be met to maintain this target. Should there be any snags along the way, ETR will advise client as early as possible to manage expectations. **Subsequent rounds as needed | 2021-11-22 | bar: Week 16 M
| 1.17 | Sitemap V1 sent for review | 2021-11-23 | bar: Week 16 T
| 1.18 | Approved sitemap sent | 2021-11-29 | bar: Week 17 M
| 1.19 | Phase 1 Complete | 2021-11-29 | bar: Week 17 M
User Experience | bar: Week 1* M
| 2 | UX/Design begins | 2021-11-23 | bar: Week 16 T
| 2.1 | UX planning & wireframing | 11/23-11/30 | bar: Week 16 T to Week 16 F; Week 17 M to Week 17 F
| 2.3 | Thanksgiving holiday | 11/25-11/26 | bar: Week 16 Th to Week 16 F
| 2.2 | Wireframes Group 1 delivery & presentation - Homepage | 2021-12-09 | bar: Week 18 Th
| 2.4 | Wireframes Group 1 R2 delivery | 2021-12-10 | bar: Week 18 F
| 2.5 | Wireframes Group 1 R2 feedback period | 12/10-12/14 | bar: Week 18 F to Week 19 T
| 2.6 | Wireframes Group 1 R2 approval required | 2021-12-14 | bar: Week 19 T
| 2.7 | Wireframes Group 2 delivery & presentation - Additional key pages | 2021-12-15 | bar: Week 19 W
| 2.8 | Wireframes Group 2 feedback period | 12/16-12/21 | bar: Week 19 W to Week 19 F; Week 20 M to Week 20 T
| 2.9 | Wireframes Group 2 R2 delivery | 2021-12-22 | bar: Week 20 W
| 2.1 | Wireframes Group 2 R2 feedback period | 12/22-12/23 | bar: Week 20 W to Week 20 Th
| 2.11 | Wireframes Group 2 R2 approval required | 2021-12-23 | bar: Week 20 Th
| 2.12 | ETR holiday week | 12/24-1/1 | bar: Week 20 F to Week 21 F
| 2.13 | Wireframes Group 3 delivery & presentation - Remaining pages | 2021-12-21 | bar: Week 20 T
| 2.14 | Wireframes Group 3 feedback period | 12/21-1/4 | bar: Week 20 T to Week 21 F; Week 22 M to Week 22 T
| 2.15 | Wireframes Group 3 R2 delivery | 2021-01-05 | bar: Week 22 W
| 2.16 | Wireframes Group 3 R2 feedback period | 1/5-1/6 | bar: Week 22 W to Week 22 Th
| 2.17 | Wireframes Group 3 R2 approval required | 2021-01-07 | bar: Week 22 F
Visual Design | bar: Week 1* M
| 3 | Visual design kick-off | 2021-12-13 | bar: Week 16 Sat to Week 16 Sun; Week 19 M
| 3.1 | Digital art direction & concepting | 12/13-12/20 | bar: Week 19 M to Week 20 M
| 3.2 | Digital art direction R1 delivery & presentation | 2021-12-20 | bar: Week 16 Sat to Week 16 Sun; Week 20 M
| 3.3 | Digital art direction R1 feedback period | 12/21-12/22 | bar: Week 20 T to Week 20 Th
| 3.4 | ETR holiday week | 12/24-1/1 | bar: Week 16 Sat to Week 16 Sun; Week 20 F to Week 21 F
| 3.5 | Digital art direction R2 delivery | 2021-01-04 | bar: Week 22 T
| 3.6 | Digital art direction R2 approval required | 2021-01-06 | bar: Week 22 Th
| 3.7 | Design Group 1 delivery & presentation - Homepage | 2021-01-10 | bar: Week 23 M
| 3.8 | Design Group 1 feedback period | 1/11-1/14 | bar: Week 23 M to Week 23 F
| 3.9 | Design Group 2 delivery & presentation | 2022-01-19 | bar: Week 24 W
| 3.1 | Design Group 2 feedback period | 1/19-1/24 | bar: Week 24 W to Week 25 M
| 3.11 | Design Group 3 delivery & presentation | 2022-01-26 | bar: Week 25 W
| 3.12 | Design Group 3 feedback period | 1/26-1/31 | bar: Week 25 W to Week 25 F; Week 26 M
| 3.13 | Design Group 3 R2 delivery | 2022-01-31 | bar: Week 26 M
| 3.14 | Design Group 3 R2 approval required | 2022-02-02 | bar: Week 26 W
| 3.15 | Design complete** | 2022-02-28 | bar: Week 30 M
Development | bar: Week 1* M
| 4 | Web development begins | 2021-01-10 | bar: Week 10 Sat to Week 10 Sun; Week 11 Sat to Week 11 Sun; Week 12 Sat to Week 12 Sun; Week 15 T to Week 21 F; Week 22 M to Week 22 F
| 4.1 | Web development process | 1/10-4/8 | bar: Week 18 W to Week 23 F
| 4.2 | Content migration of any legacy content (posts/articles/news) | 3/30-4/1 | bar: Week 22 F
| 4.2 | Legal & compliance review - key pages | 4/1-4/11 | bar: Week 23 F
| 4.3 | Migrated content review | 4/4-4/8 | bar: Week 25 M
| 4.4 | Prod hosting environment in place | 2021-04-06 | bar: Week 25 M to Week 25 F; Week 26 M to Week 26 F; Week 27 M to Week 27 F; Week 28 M to Week 28 F; Week 29 M to Week 29 F; Week 30 M to Week 30 F; Week 31 M to Week 31 F; Week 32 M to Week 32 F; Week 33 M to Week 33 F; Week 34 M to Week 34 F; Week 35 M to Week 35 F
| 4.8 | Tracking/analytics specifications required | 2021-04-06 | bar: Week 34 W to Week 34 F
| 4.9 | UAT (incl QA of FE/BE, forms, and browser comp.) | 4/11-5/3 | bar: Week 34 F; Week 35 M to Week 35 F; Week 36 M
| 4.1 | Beta release - staging site | 2022-04-18 | bar: Week 35 M to Week 35 F
| 4.11 | CMS training (tentative) | 2021-04-20 | bar: Week 35 W
| 4.12 | Input of approved content into CMS | 4/20-5/3 | bar: Week 35 W
| 4.13 | Content sign-off by core team | 2021-05-03 | bar: Week 13 Sat to Week 13 Sun; Week 36 M to Week 37 F; Week 38 M to Week 38 F; Week 39 M to Week 39 T
| 4.14 | Legal, compliance, & ELT review | 5/4-5/18 | bar: Week 37 M
| 4.15 | Application signoff for release | 2022-05-18 | bar: Week 37 W
| 4.17 | Site launch target - Phase 1.0 complete | 2022-05-18 | bar: Week 37 W to Week 39 T
| 4.18 | Post-launch releases and site support begin | 2022-05-18 | bar: Week 38 Sat to Week 38 Sun; Week 39 T; Week 39 Sat to Week 39 Sun
Note: *Milestones must be met to maintain this target. Should there be any snags along the way, ETR will advise client as early as possible to manage expectations. **Subsequent rounds as needed | bar: Week 1* M

## Functional Requirements
Functional Requirements
The functional requirements represent features and interactions that can occur on the site and need to be accounted for in scope planning. These requirements exclude passive content requirements such as reading or browsing information. In order to ensure we have captured every functional requirement, please make sure nothing is missing.
ID | Area | User Type Focus | Functional Requirement | Acceptance Criteria | Notes | User Need | Business Need
1 | CMS | Admin | Ability to edit information through a content management system with no need to use code.
2
3
4

## Technical Requirements
Technical Requirements
The technical requirements represent specific technical or compliancy needs identified during discovery that will be included in the final deliverables.
ID | Area | Technical Requirement | Notes
1 | CMS/FE | Responsively designed to adjust to multiple screen breakpoints
2
3

## User Types & Top Needs
User Types & Top Needs
User Type | General Description | Top Scenarios | Top User Needs

## Web Content Project Plan
Web Content Project Plan
Pages |  | Page Details |  |  |  | Content |  |  |  |  | Metadata |  | Notes
Web Section | Page [Sitemap reference] | Page Type | Wireframe URL (if available) | Admin URL | URL - Staging | Copy Writer | Copy Status | Staging Reviews | Assignee | Copy Document or Design Link | Page Meta Title (70 characters or less) | Page Meta Description (160 characters or less) | Notes
Homepage | Home Page | Homepage |  |  |  |  | Not started | Not started
About | Landing Page 1 | Landing Page |  |  |  |  | Not started | Not started
About | Sub-page 1 | Basic WYSIWYG |  |  |  |  | Not started | Not started
About | Sub-page 2 | Basic WYSIWYG |  |  |  |  | Not started | Not started

## Redirect Mapping
Redirect Mapping
Origin | Target | Type | Format
|  | 301 | plain
|  | 301 | plain
|  | 301 | plain

## QA List
Redirect Mapping
Task List |  |  |  |  | Notes
Issue | Priority | Owner | Status | URL (if applicable) | Notes
Task 1 | P1 | ETR | Not started
QA item 2 | P2 | ETR | Not started
Task 3 | P3 | ETR | Not started
QA Iitem 4 | P4 | ETR | Not started